## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup & Repository Initialization | MUST HAVE | VS Code, Git | Sibitha Namakkal Ravikumar | 3- Completed
S1 | S1 | US-002 | Backend Setup using FastAPI and Uvicorn | MUST HAVE | Python 3.8+, Pip | Sibitha Namakkal Ravikumar | 3- Completed
S2 | S2 | US-003 | Integration of APIs (GNews,Twitter) | MUST HAVE | API Keys | Sibitha Namakkal Ravikumar | 3- Completed
S2 | S2 | US-004 | OpenAI GPT & LLaMA Integration for NLP | SHOULD HAVE | OpenAI API Key | Sibitha Namakkal Ravikumar | 3- Completed
S3 | S3 | US-005 | Data Collection Pipeline Initialization | MUST HAVE | Pandas, Requests | Sibitha Namakkal Ravikumar | 3- Completed
S3 | S3 | US-006 | Data Cleaning & Sentiment Computation | MUST HAVE | TextBlob, NumPy | Sibitha Namakkal Ravikumar | 3- Completed
S4 | S4 | US-007 | Trend Forecasting Model Development | SHOULD HAVE | Prophet | Sibitha Namakkal Ravikumar | 3- Completed
S4 | S4 | US-008 | Alert System Configuration (spikes, sentiment, trends) | MUST HAVE | Slack Webhook | Sibitha Namakkal Ravikumar | 3- Completed
S5 | S5 | US-009 | Frontend Development (React) | MUST HAVE | Node.js, npm | Sibitha Namakkal Ravikumar | 3- Completed
S5 | S5 | US-010 | Dashboard UI Design & Chart Visualization | MUST HAVE | Recharts, Lucide Icons | Sibitha Namakkal Ravikumar | 3- Completed
S6 | S6 | US-011 | Competitor & Domain Selector Modal | COULD HAVE | React Modal, Context API | Sibitha Namakkal Ravikumar | 3- Completed
S6 | S6 | US-012 | Customizable Filters (Time Range, Sentiment, Source) | SHOULD HAVE | React State Management | Sibitha Namakkal Ravikumar | 3- Completed
S7 | S7 | US-013 | API–Frontend Integration | MUST HAVE | CORS Middleware | Sibitha Namakkal Ravikumar | 3- Completed
S7 | S7 | US-014 | Alert Visualization and Notification Center | SHOULD HAVE | Slack API | Sibitha Namakkal Ravikumar | 3- Completed
S8 | S8 | US-015 | Testing of Data APIs and Alert Logic | MUST HAVE | Postman, cURL | Sibitha Namakkal Ravikumar | 3- Completed
S8 | S8 | US-016 | Dashboard Deployment | MUST HAVE | Render, GitHub CI/CD | Sibitha Namakkal Ravikumar | 3- Completed
S9 | S9 | US-017 | News Feed Page with Filtering Options | MUST HAVE | News API Data | Sibitha Namakkal Ravikumar | 3- Completed
S10 | S10 | US-018 | Social Media Sentiment Analytics Page | MUST HAVE | Reddit & Twitter API | Sibitha Namakkal Ravikumar | 3- Completed
S10 | S10 | US-019 | Competitor Insights Panel with Metrics | SHOULD HAVE | Chart Components | Sibitha Namakkal Ravikumar | 3- Completed
S11 | S11 | US-020 | Export Feature for Reports and Data Charts | COULD HAVE | CSV Export Package | Sibitha Namakkal Ravikumar | 3- Completed
S11 | S11 | US-021 | Data Validation and Error Handling System | MUST HAVE | Exception Logging | Sibitha Namakkal Ravikumar | 3- Completed
S12 | S12 | US-022 | Real-time Alert Push via Slack Webhook | SHOULD HAVE | Slack API | Sibitha Namakkal Ravikumar | 3- Completed
S12 | S12 | US-023 | Automated Data Refresh & Caching Mechanism | COULD HAVE | LocalStorage, Cache | Sibitha Namakkal Ravikumar | 3- Completed
S13 | S13 | US-024 | Final Report & Presentation Preparation | MUST HAVE | PowerPoint, Canva | Sibitha Namakkal Ravikumar | 3- Completed
S13 | S13 | US-025 | User Onboarding Documentation | SHOULD HAVE | Readme, Docsify | Sibitha Namakkal Ravikumar | 3- Completed
S14 | S14 | US-026 | Competitor Benchmark Comparison Table | COULD HAVE | Table Library | Sibitha Namakkal Ravikumar | 3- Completed
S14 | S14 | US-027 | Interactive Trend Timelines | SHOULD HAVE | Plotly, Matplotlib | Sibitha Namakkal Ravikumar | 3- Completed
S15 | S15 | US-028 | Insight Export to PDF | COULD HAVE | ReportLab | Sibitha Namakkal Ravikumar | 3- Completed
S15 | S15 | US-029 | Alerts Export to PDF | COULD HAVE | ReportLab | Sibitha Namakkal Ravikumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 111 | 49 | 58 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Set up API configurations and data collection functions | 2025-08-20 | 2025-08-21 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Implement data collection from NewsAPI | 2025-08-22 | 2025-08-23 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Implement data collection from Reddit | 2025-08-24 | 2025-08-25 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Implement data collection from GNEWS | 2025-08-26 | 2025-08-27 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 5 | Create data preprocessing functions | 2025-08-28 | 2025-08-29 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 6 | Implement text cleaning and normalization | 2025-08-30 | 2025-08-31 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 7 | Handle missing data and duplicates | 2025-09-01 | 2025-09-02 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 8 | Set up model for sentiment analysis | 2025-09-03 | 2025-09-05 | Sibiha Namakkal Ravikumar | ML Integration | 3- Completed | 6 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 9 | Implement sentiment scoring system | 2025-09-06 | 2025-09-07 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 10 | Test sentiment analysis on sample data | 2025-09-08 | 2025-09-09 | Sibiha Namakkal Ravikumar | Testing | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 11 | Implement Prophet forecasting model | 2025-09-10 | 2025-09-12 | Sibiha Namakkal Ravikumar | ML Integration | 3- Completed | 7 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 12 | Create forecast visualization components | 2025-09-13 | 2025-09-14 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 13 | Set up alert thresholds and conditions | 2025-09-15 | 2025-09-16 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 14 | Implement Slack integration for alerts | 2025-09-17 | 2025-09-19 | Sibiha Namakkal Ravikumar | Integration | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 15 | Design main dashboard layout | 2025-09-20 | 2025-09-22 | Sibiha Namakkal Ravikumar | Design | 3- Completed | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 16 | Implement sentiment timeline visualization | 2025-09-23 | 2025-09-24 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 17 | Create source analysis charts | 2025-09-25 | 2025-09-26 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 18 | Implement trend analysis features | 2025-09-27 | 2025-09-28 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 19 | Prepare requirements.txt for deployment | 2025-09-29 | 2025-09-30 | Sibiha Namakkal Ravikumar | Deployment | 3- Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 20 | Deploy to Streamlit Cloud | 2025-10-01 | 2025-10-03 | Sibiha Namakkal Ravikumar | Deployment | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 21 | Implement sample data generation | 2025-10-04 | 2025-10-05 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 22 | Add error handling for missing files | 2025-10-06 | 2025-10-07 | Sibiha Namakkal Ravikumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 23 | Design competitor analysis features | 2025-10-08 | 2025-10-09 | Sibiha Namakkal Ravikumar | Design | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | API rate limiting issues with NewsAPI | Implemented error handling and request delays
Sprint 1 | Day 4 | Difficulty handling different date formats from various APIs | Created unified date parsing function
Sprint 2 | Day 6 | model loading slowly on first run | Added model caching and pre-loading
Sprint 2 | Day 8 | Memory issues with large datasets | Implemented data chunking and garbage collection
Sprint 3 | Day 12 | Prophet forecasting giving inconsistent results | Adjusted model hyperparameters and validation
Sprint 3 | Day 14 | Dashboard performance issues with large datasets | Fixed Requirement.txt
Sprint 4 | Day 18 | Streamlit deployment failing due to dependency conflicts | Optimized data aggregation and plotting
Sprint 4 | Day 20 | File not found errors on fresh deployment | Added sample data generation and better error handling
Sprint 5 | Day 24 | Complex competitor analysis visualization requirements | Researching better charting libraries and approaches

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-20 | 2025-09-02 | Sibitha Namakkal Ravikumar | Writing comprehensive unit tests for each module | Underestimating API integration complexity | Regular code reviews and documentation | Implemented test suite for data collection modules
2 | Sprint 2 | 2025-09-03 | 2025-09-19 | Sibitha Namakkal Ravikumar | Performance benchmarking for ML models | Loading large models without caching | Monitoring memory usage during development | Added model caching and memory optimization
3 | Sprint 3 | 2025-09-20 | 2025-10-05 | Sibitha Namakkal Ravikumar | Creating backup data sources for API failures | Hardcoding configuration values | Regular deployment testing | Implemented configuration management system
4 | Sprint 4 | 2025-10-06 | 2025-10-13 | Sibitha Namakkal Ravikumar | Monitoring application performance in production | Manual deployment processes | Automated testing before deployment | Set up CI/CD pipeline for Streamlit deployment