## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup & Repository Initialization | MUST HAVE | VS Code, Git | Sibitha Namakkal Ravikumar | 3- Completed
S1 | S1 | US-002 | Backend Setup using FastAPI and Uvicorn | MUST HAVE | Python 3.8+, Pip | Sibitha Namakkal Ravikumar | 3- Completed
S2 | S2 | US-003 | Integration of APIs (GNews,Twitter) | MUST HAVE | API Keys | Sibitha Namakkal Ravikumar | 3- Completed
S2 | S2 | US-004 | OpenAI GPT & LLaMA Integration for NLP | SHOULD HAVE | OpenAI API Key | Sibitha Namakkal Ravikumar | 3- Completed
S3 | S3 | US-005 | Data Collection Pipeline Initialization | MUST HAVE | Pandas, Requests | Sibitha Namakkal Ravikumar | 3- Completed
S3 | S3 | US-006 | Data Cleaning & Sentiment Computation | MUST HAVE | TextBlob, NumPy | Sibitha Namakkal Ravikumar | 3- Completed
S4 | S4 | US-007 | Trend Forecasting Model Development | SHOULD HAVE | Prophet | Sibitha Namakkal Ravikumar | 3- Completed
S4 | S4 | US-008 | Alert System Configuration (spikes, sentiment, trends) | MUST HAVE | Slack Webhook | Sibitha Namakkal Ravikumar | 3- Completed
S5 | S5 | US-009 | Frontend Development (React) | MUST HAVE | Node.js, npm | Sibitha Namakkal Ravikumar | 3- Completed
S5 | S5 | US-010 | Dashboard UI Design & Chart Visualization | MUST HAVE | Recharts, Lucide Icons | Sibitha Namakkal Ravikumar | 3- Completed
S6 | S6 | US-011 | Competitor & Domain Selector Modal | COULD HAVE | React Modal, Context API | Sibitha Namakkal Ravikumar | 3- Completed
S6 | S6 | US-012 | Customizable Filters (Time Range, Sentiment, Source) | SHOULD HAVE | React State Management | Sibitha Namakkal Ravikumar | 3- Completed
S7 | S7 | US-013 | API–Frontend Integration | MUST HAVE | CORS Middleware | Sibitha Namakkal Ravikumar | 3- Completed
S7 | S7 | US-014 | Alert Visualization and Notification Center | SHOULD HAVE | Slack API | Sibitha Namakkal Ravikumar | 3- Completed
S8 | S8 | US-015 | Testing of Data APIs and Alert Logic | MUST HAVE | Postman, cURL | Sibitha Namakkal Ravikumar | 3- Completed
S8 | S8 | US-016 | Dashboard Deployment | MUST HAVE | Render, GitHub CI/CD | Sibitha Namakkal Ravikumar | 3- Completed
S9 | S9 | US-017 | News Feed Page with Filtering Options | MUST HAVE | News API Data | Sibitha Namakkal Ravikumar | 3- Completed
S10 | S10 | US-018 | Social Media Sentiment Analytics Page | MUST HAVE | Reddit & Twitter API | Sibitha Namakkal Ravikumar | 3- Completed
S10 | S10 | US-019 | Competitor Insights Panel with Metrics | SHOULD HAVE | Chart Components | Sibitha Namakkal Ravikumar | 3- Completed
S11 | S11 | US-020 | Export Feature for Reports and Data Charts | COULD HAVE | CSV Export Package | Sibitha Namakkal Ravikumar | 3- Completed
S11 | S11 | US-021 | Data Validation and Error Handling System | MUST HAVE | Exception Logging | Sibitha Namakkal Ravikumar | 3- Completed
S12 | S12 | US-022 | Real-time Alert Push via Slack Webhook | SHOULD HAVE | Slack API | Sibitha Namakkal Ravikumar | 3- Completed
S12 | S12 | US-023 | Automated Data Refresh & Caching Mechanism | COULD HAVE | LocalStorage, Cache | Sibitha Namakkal Ravikumar | 3- Completed
S13 | S13 | US-024 | Final Report & Presentation Preparation | MUST HAVE | PowerPoint, Canva | Sibitha Namakkal Ravikumar | 3- Completed
S13 | S13 | US-025 | User Onboarding Documentation | SHOULD HAVE | Readme, Docsify | Sibitha Namakkal Ravikumar | 3- Completed
S14 | S14 | US-026 | Competitor Benchmark Comparison Table | COULD HAVE | Table Library | Sibitha Namakkal Ravikumar | 3- Completed
S14 | S14 | US-027 | Interactive Trend Timelines | SHOULD HAVE | Plotly, Matplotlib | Sibitha Namakkal Ravikumar | 3- Completed
S15 | S15 | US-028 | Insight Export to PDF | COULD HAVE | ReportLab | Sibitha Namakkal Ravikumar | 3- Completed
S15 | S15 | US-029 | Alerts Export to PDF | COULD HAVE | ReportLab | Sibitha Namakkal Ravikumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7